# Odoo 19 Implementation Task Plan

## Ready-Made Doors, Frames, Hardware and Accessories Trading - Iraq

Three locations | 17+ core users | Sales, POS, Inventory, Purchase, Quality and Finance

Version 1.0 | 11 July 2026 | Planning baseline for discovery and implementation

Prepared from standard_tasks.xlsx, the local Odoo 19 Community/Enterprise source, and a read-only review of the supplied Odoo.sh furniture reference database using the codex_odoo_sh identity. Custom code in that reference was deliberately not treated as a requirements baseline.

# 1. Executive summary

The target solution is a trading and distribution system, not a manufacturing or field-installation system. Odoo will control imported and locally purchased ready-made doors and components, inventory across three physical sites, light in-house customization sold as services, showroom POS, wholesale/contractor credit sales, delivery, driver cash, landed cost, quality release, and segregated accounting.

The recommended approach is Odoo 19 Enterprise with standard applications as the accounting and operational backbone, plus a small, controlled set of custom addons for requirements that must block, aggregate or orchestrate transactions across applications. Studio alone should not be used for accounting-critical security or blocking logic.

The furniture reference supports this direction: standard Sales, Purchase, Inventory, POS, Accounting, Quality, Approvals, Expenses, Documents, Dashboards and Landed Costs are installed; it also demonstrates multiple POS configurations, multiple cash/driver-style journals, Arabic labels and separate Color, Size and Height attributes. It has only one warehouse, so its topology must not be copied; this design requires three warehouses and transit controls.

# 2. Business and solution boundaries

- Included: import/local purchasing, warehousing, internal transfers, sales, POS, delivery handover, returns, light customization charges, quality, accounting, landed cost, expenses, driver cash, approvals and dashboards.

- Excluded: raw-material manufacturing, bills of materials, work orders, MRP costing, construction-site installation, field-service dispatch and engineering crews.

- Light customization is handled as service lines and controlled workshop/quality statuses. Detailed capacity or work-center planning is future scope.

- Iraqi tax and withholding configuration requires written validation by the client chief accountant/tax adviser.

# 3. Standard-versus-extension decision

| Requirement | Recommended treatment | Reason |
| --- | --- | --- |
| Variants, RAL/size attributes, quantities, incoming and forecast | Standard foundation + custom search/panel | Core data is standard; separated filters and consolidated branch presentation need tailored UI. |
| Quantity discounts | Standard pricelists | Minimum-quantity rules cover the agreed tiers. |
| Discount and credit approvals | Custom chained approval | Freeze transaction and require AR then one Owner with audit evidence. |
| Quality checks | Enterprise Quality + custom release block | Checks are standard; absolute delivery/POS enforcement requires extension. |
| Landed costs and FX | Standard | Configure and reconcile standard accounting/inventory capabilities. |
| Fast transfer manifest | Barcode + custom manifest action | Keep standard transfers as truth; remove line-by-line receipt entry. |
| Customer 360 and branch stock | Custom read-only panels | Information spans accounting, sales, POS and inventory. |
| Driver cash boxes | Cash journals + custom COD/handover | Journals hold balances; delivery assignment, counted handover and variance need workflow. |
| Expense matching | Standard reconciliation models | Recurring descriptions can propose accounts and analytics. |
| Light customization | Service products + small workflow | Avoid MRP while guaranteeing price capture and quality status. |

# 4. Delivery gates and acceptance

- Gate 0: scope and governance approved.

- Gate 1: discovery and fit-gap blueprint signed.

- Gate 2: foundation, security and master-data design accepted.

- Gate 3: configured prototype and custom specifications approved.

- Gate 4: testing and migration rehearsal pass.

- Gate 5: training and UAT signed.

- Gate 6: go-live readiness and opening reconciliations approved.

- Gate 7: hypercare closed and handover accepted.

Acceptance requires configured evidence, tests, reconciliations, negative-access checks where relevant, issue closure and named client approval.

# 5. Detailed implementation task register

Each item is a deliverable-bearing task. â€œExtensionâ€ includes Studio only where safe; accounting-critical, blocking, security and cross-application logic requires a version-controlled addon.

## P0 - Mobilization and governance

| ID | Task | Responsible | Treatment | Deliverable / acceptance evidence |
| --- | --- | --- | --- | --- |
| 001 | Confirm commercial scope, objectives, success measures, exclusions and change-control procedure | Project Manager | Standard | Signed scope baseline and KPI list |
| 002 | Appoint sponsor, steering committee, process owners, key users, data owners and backups | Project Manager | Standard | Approved responsibility matrix |
| 003 | Create project workspace, decision log, issue/risk log, change register and weekly cadence | Project Manager | Standard | Project controls operational |
| 004 | Confirm Odoo.sh production, staging and development branches, access and backup policy | Technical Lead | Standard | Environment readiness record |
| 005 | Document reusable configuration patterns from the furniture reference database and validate which apply to the doors business | Functional Lead | Reference reviewed | Reference review report |
| 006 | Confirm Arabic/English language, Asia/Baghdad timezone, IQD base currency and USD transaction currency | Chief Accountant | Standard | Localization decision sheet |
| 007 | Run kickoff and approve detailed discovery calendar for all 17+ core users | Project Manager | Standard | Kickoff minutes and workshop plan |

## P1 - Discovery and solution blueprint

| ID | Task | Responsible | Treatment | Deliverable / acceptance evidence |
| --- | --- | --- | --- | --- |
| 010 | Map lead/quotation/POS/order/delivery/return processes for retail, wholesale and contractors | Sales Lead | Standard | Signed sales process map |
| 011 | Map foreign and local purchasing, container tracking, receipt and three-way-match controls | AP Accountant | Standard | Signed procure-to-pay map |
| 012 | Map three-site stock topology, receipts, internal transfers, reservations, dispatch and counts | Inventory Lead | Standard | Signed warehouse map |
| 013 | Define door customization intake, pricing, workshop status and handover without MRP or field service | Operations Lead | Extension | Approved light-customization blueprint |
| 014 | Define quality criteria by product family and the exact mandatory release gate | Inventory Lead | Extension | Quality control matrix |
| 015 | Define AR, AP, driver cash, bank, expenses, landed cost, FX, tax and closing processes | Chief Accountant | Standard + extension | Finance blueprint |
| 016 | Define branch profitability dimensions, analytic accounts/plans and executive reporting KPIs | Chief Accountant | Standard | Management reporting blueprint |
| 017 | Define discount tiers, exception thresholds, credit limits and two-stage approval authority | Owners + AR Accountant | Extension | Approval authority matrix |
| 018 | Profile all legacy data sources, volumes, quality, duplicates and historical retention needs | Data Lead | Standard | Data assessment report |
| 019 | Approve fit-gap register classifying every requirement as standard, configuration, Studio, custom or excluded | Steering Committee | Standard | Signed solution blueprint |

## P2 - Platform, company and security foundation

| ID | Task | Responsible | Treatment | Deliverable / acceptance evidence |
| --- | --- | --- | --- | --- |
| 020 | Install and validate Sales, Purchase, Inventory, Barcode, POS, Accounting, Contacts, Quality, Approvals, Expenses, Documents and Dashboards | Technical Lead | Standard Enterprise | Installed-app baseline |
| 021 | Keep MRP, Project-based field installation and Field Service outside operational scope | Functional Lead | Explicit exclusion | No unintended manufacturing/service flow |
| 022 | Configure legal company profile, addresses, logo, document layout, languages and currencies | Functional Lead | Standard | Approved company setup |
| 023 | Create 3 warehouses: Main Warehouse, Branch 1 and Branch 2 with internal/transit locations | Inventory Consultant | Standard | Warehouse topology tested |
| 024 | Configure sequences by warehouse/branch for quotations, POS, receipts, deliveries, transfers and journals | Functional Lead | Standard | Traceable numbering scheme |
| 025 | Create 17+ named users and assign least-privilege application access | Administrator | Standard | User register |
| 026 | Implement segregated accounting roles for AR, AP, driver treasury, inventory cost, tax/expenses, bank reconciliation and chief accountant | Technical Lead | Custom security | Negative-access tests pass |
| 027 | Restrict each warehouse specialist to intended operational locations while preserving approved cross-branch visibility | Technical Lead | Custom security | Warehouse access tests pass |
| 028 | Configure owners as read-only executive users with approval rights and dashboards | Administrator | Configuration + extension | Executive access accepted |
| 029 | Enable audit-friendly chatter, activities, document attachments and approval evidence retention | Functional Lead | Standard | Audit trail convention |
| 030 | Execute security test matrix: allowed actions, prohibited actions and escalation paths for every role | QA Lead | Standard | Signed segregation-of-duties test |

## P3 - Master data and product architecture

| ID | Task | Responsible | Treatment | Deliverable / acceptance evidence |
| --- | --- | --- | --- | --- |
| 031 | Design product category hierarchy for doors, frames, panels, locks, accessories, glass and services | Product Data Owner | Standard | Approved category tree |
| 032 | Define stockable products versus non-stock service products and accounting properties | Inventory Accountant | Standard | Product-type matrix |
| 033 | Create independent attributes for color/finish, RAL code, width, height, frame size, handing and model | Product Data Owner | Standard | Attribute dictionary |
| 034 | Decide variant-generation rules to avoid unnecessary SKU explosion and archive invalid combinations | Product Data Owner | Standard | Variant policy |
| 035 | Define SKU, barcode and display-name conventions supporting Arabic/English search | Product Data Owner | Standard | Naming convention |
| 036 | Add normalized searchable RAL/color and dimension fields and filters to product, sales and POS selection | Technical Lead | Custom UI/search | Independent search accepted |
| 037 | Configure units of measure, packaging, supplier codes, lead times, minimum quantities and purchase prices | Purchase Lead | Standard | Supplier data ready |
| 038 | Configure AVCO or FIFO decision by category, automated valuation, stock/input/output and price-difference accounts | Inventory Accountant | Standard | Valuation setup approved |
| 039 | Create customization service catalog: trimming, lock drilling, glass insertion and RAL spraying with IQD prices | Sales Lead | Standard | Service catalog |
| 040 | Configure optional accessory/customization prompts when a door is added to quotation or POS | Technical Lead | Custom UX | Add-on prompt test passes |
| 041 | Prepare controlled import templates for products, variants, barcodes, suppliers, contacts and price lists | Data Lead | Standard | Approved templates |
| 042 | Cleanse, deduplicate, trial-import and reconcile master data counts | Data Lead | Standard | Migration rehearsal report |

## P4 - Sales, POS, pricing and customer controls

| ID | Task | Responsible | Treatment | Deliverable / acceptance evidence |
| --- | --- | --- | --- | --- |
| 043 | Configure sales teams by branch, quotation templates, validity, payment terms and delivery policy | Sales Consultant | Standard | Sales setup tested |
| 044 | Configure two POS terminals, cash/card/customer-account methods, receipts, taxes and session controls | POS Consultant | Standard | Branch POS pilots pass |
| 045 | Configure quantity-based pricelist breaks: 1-4 standard, 5-9 5%, 10-19 10%, 20+ 15% | Sales Consultant | Standard | Price tests pass at boundaries |
| 046 | Prevent unauthorized manual discounts and log requested versus permitted discount | Technical Lead | Extension | Discount control test passes |
| 047 | Build sequential exception approval: AR Accountant then one Owner for excess discount or credit exposure | Technical Lead | Custom workflow | Approval, rejection and timeout tests pass |
| 048 | Configure customer credit limits, payment terms, overdue policy and warning/block thresholds | AR Accountant | Standard + extension | Credit-control matrix accepted |
| 049 | Build customer 360 action from Sales and POS showing invoices, debt, limits, purchases and exact variants | Technical Lead | Custom UI | Customer history acceptance test |
| 050 | Build cross-branch availability panel showing on hand, reserved, available, incoming and sold by warehouse | Technical Lead | Custom UI/report | Three-warehouse quantities reconcile |
| 051 | Configure reservations, partial fulfillment, backorders, branch sourcing and customer promises | Sales + Inventory Leads | Standard | Allocation scenarios pass |
| 052 | Configure quotation/order cancellation, returns, refunds, exchanges and damaged-goods handling | Functional Lead | Standard | Exception scenarios pass |
| 053 | Configure delivery orders with driver assignment and cash-on-delivery payment expectation | Functional Lead | Extension | COD traceability test |
| 054 | Validate retail, wholesale, contractor, mixed payment, credit, return and customization end-to-end scenarios | QA Lead | Standard | Sales/POS test pack signed |

## P5 - Purchase, imports and landed cost

| ID | Task | Responsible | Treatment | Deliverable / acceptance evidence |
| --- | --- | --- | --- | --- |
| 055 | Configure local/foreign vendors, USD/IQD price lists, incoterms, lead times and purchase agreements | Purchase Consultant | Standard | Vendor purchasing setup |
| 056 | Configure RFQ/PO approval limits including high-value owner approval | Technical Lead | Approvals/configuration | Purchase approval tests pass |
| 057 | Configure purchase receipt and vendor bill control policy for three-way matching | AP Accountant | Standard | PO/receipt/bill tolerance tests |
| 058 | Model container/import reference, ETD, ETA, carrier, customs status and document attachments | Technical Lead | Studio or custom | Shipment tracker accepted |
| 059 | Configure incoming quantities and expected dates from confirmed purchase orders | Purchase Consultant | Standard | Incoming stock visibility validated |
| 060 | Configure landed-cost service products for freight, customs, clearance and offloading | Inventory Accountant | Standard | Landed-cost catalog |
| 061 | Define and test landed-cost allocation methods and accounting postings by receipt/container | Inventory Accountant | Standard | Cost allocation reconciliation |
| 062 | Configure foreign-currency bills, exchange rates, realized/unrealized differences and payment scheduling | Chief Accountant | Standard | FX accounting tests pass |
| 063 | Test partial receipt, damaged receipt, short shipment, extra charges, return-to-vendor and bill variance | QA Lead | Standard | Procure-to-pay UAT signed |

## P6 - Inventory, transfers, barcode and quality

| ID | Task | Responsible | Treatment | Deliverable / acceptance evidence |
| --- | --- | --- | --- | --- |
| 064 | Configure receipts, deliveries, internal transfers, transit locations and branch replenishment routes | Inventory Consultant | Standard | Operation types validated |
| 065 | Configure barcode nomenclature, product labels, package/transfer sheet barcodes and scanners | Barcode Consultant | Standard + extension | Barcode pilot passes |
| 066 | Create digital transfer manifest with batch lines and a single scan/open action | Technical Lead | Custom | Manifest generated and traceable |
| 067 | Implement one-click/batch validation at receiving branch with discrepancy capture, not blind acceptance | Technical Lead | Custom | Rapid transfer acceptance test |
| 068 | Validate real-time origin, transit and destination balances during every transfer state | QA Lead | Standard | Transfer quantity reconciliation |
| 069 | Configure putaway/storage conventions, damaged/quarantine locations and scrap policy | Inventory Lead | Standard | Location controls accepted |
| 070 | Configure quality control points for receipt, pre-delivery and POS handover by product family | Quality Consultant | Standard Enterprise | Quality points active |
| 071 | Configure checks for dimensions, paint integrity, warping, accessories, glass and lock preparation | Quality Consultant | Standard | Check templates approved |
| 072 | Implement hard block preventing delivery/POS handover while quality is pending or failed | Technical Lead | Custom blocking rule | Negative release tests pass |
| 073 | Configure quality alerts, quarantine, rework/customization return, downgrade and manager disposition | Quality Consultant | Standard + extension | Failed-quality workflow passes |
| 074 | Configure cycle counts, annual inventory, count tolerances and approval of adjustments | Inventory Accountant | Standard | Count procedure and tests |
| 075 | Configure reordering rules using on-hand, forecast and incoming demand without double ordering | Inventory Planner | Standard | Replenishment scenarios pass |
| 076 | Reconcile inventory valuation, stock cards and branch quantities after all inventory scenarios | Inventory Accountant | Standard | Inventory control signoff |

## P7 - Finance, treasury, tax and expenses

| ID | Task | Responsible | Treatment | Deliverable / acceptance evidence |
| --- | --- | --- | --- | --- |
| 077 | Design and import Iraqi chart of accounts with account groups and control accounts | Chief Accountant | Localization/configuration | COA approved |
| 078 | Configure sales, purchase, cash, bank, card, driver and miscellaneous journals with sequences | Chief Accountant | Standard | Journal matrix |
| 079 | Configure IQD rounding, USD transactions, exchange-rate policy and multi-currency reporting | Chief Accountant | Standard | Currency tests pass |
| 080 | Configure sales and purchase tax treatment and validate Iraqi statutory requirements with client tax adviser | Tax Accountant | Configuration | Tax signoff; legal advice retained by client |
| 081 | Configure 3.3% supply and 7% service withholding logic, certificates and reporting where applicable | Technical Lead + Tax Accountant | Localization/custom | Withholding scenarios pass |
| 082 | Configure AR invoicing, receipts, aging, follow-up, credit notes and branch cash verification | AR Accountant | Standard | AR month simulation |
| 083 | Configure AP bills, payment schedules, vendor statements, refunds and three-way-match review | AP Accountant | Standard | AP month simulation |
| 084 | Create a dedicated virtual cash journal/box for each delivery driver | Treasury Accountant | Standard design | Driver journals operational |
| 085 | Implement driver collection posting from delivered COD order to assigned driver box | Technical Lead | Custom workflow | Collection traceability test |
| 086 | Implement daily driver statement, counted cash, central-vault transfer and over/short variance approval | Technical Lead | Custom workflow/report | Daily handover signoff test |
| 087 | Configure branch petty cash, employee advances, settlements, fuel and vehicle expenses | Expense Accountant | Standard | Expense workflows pass |
| 088 | Configure reconciliation models for recurring fuel, porter, hospitality and branch cost-center coding | Bank Reconciliation Analyst | Standard | Auto-matching sample accuracy accepted |
| 089 | Configure bank/card statement import format, reconciliation, outstanding accounts and terminal clearing | Bank Reconciliation Analyst | Standard | Bank and card reconciliation test |
| 090 | Configure analytic plans/accounts for Main, Branch 1, Branch 2, delivery and workshop customization | Chief Accountant | Standard | Analytic allocation tests |
| 091 | Configure fiscal periods, lock dates, accruals, inventory close, FX revaluation and month-end checklist | Chief Accountant | Standard | Mock close completed |
| 092 | Validate trial balance, P&L, balance sheet, cash flow, partner ledger, aging, tax and inventory valuation | Chief Accountant | Standard | Financial report signoff |

## P8 - Reporting and management control

| ID | Task | Responsible | Treatment | Deliverable / acceptance evidence |
| --- | --- | --- | --- | --- |
| 093 | Create executive dashboard for consolidated sales, gross margin, cash, receivables, payables and inventory | BI Consultant | Standard dashboard | Owner dashboard accepted |
| 094 | Create branch profitability view using revenue, COGS, discounts, expenses and analytic allocations | BI Consultant | Standard + report extension | Branch P&L reconciles to GL |
| 095 | Create inventory control dashboard for on hand, reserved, available, incoming, aging, slow stock and reorder risk | BI Consultant | Standard dashboard | Inventory dashboard accepted |
| 096 | Create shipment/container tracker for PO value, ETA, received status and landed-cost completion | BI Consultant | Custom report | Shipment tracker accepted |
| 097 | Create discount and credit-exception dashboard with approval turnaround and overrides | BI Consultant | Custom report | Control dashboard accepted |
| 098 | Create driver cash dashboard for open collections, handovers, variances and overdue cash | BI Consultant | Custom report | Treasury dashboard accepted |
| 099 | Configure saved filters and scheduled reports for each executive/accounting/warehouse role | Functional Lead | Standard | Role reporting pack |

## P9 - Data migration and cutover

| ID | Task | Responsible | Treatment | Deliverable / acceptance evidence |
| --- | --- | --- | --- | --- |
| 100 | Approve migration scope, cut-off dates, ownership, reconciliation rules and rollback criteria | Data Lead | Standard | Migration strategy |
| 101 | Clean and import customers, suppliers, contacts, credit terms and credit limits | Data Lead | Standard | Contact reconciliation |
| 102 | Clean and import products, variants, RAL/dimensions, barcodes, vendor data and opening prices | Data Lead | Standard | Product reconciliation |
| 103 | Import opening stock by warehouse/location/variant and reconcile quantities and valuation | Inventory Accountant | Standard | Signed stock reconciliation |
| 104 | Import open sales orders, purchase orders and in-transit shipments as agreed | Data Lead | Standard | Open-document reconciliation |
| 105 | Import open AR/AP items, advances, driver balances, petty cash, bank and GL opening balances | Chief Accountant | Standard | Opening trial balance signoff |
| 106 | Perform at least two full migration rehearsals and record timing, errors and corrections | Data Lead | Standard | Rehearsal reports |
| 107 | Freeze legacy data, execute final extraction/import and archive signed source files | Project Manager | Standard | Cutover data pack |
| 108 | Run post-load reconciliation: record counts, stock, subledgers, journals and trial balance | Chief Accountant | Standard | Go-live reconciliation certificate |

## P10 - Technical development and release assurance

| ID | Task | Responsible | Treatment | Deliverable / acceptance evidence |
| --- | --- | --- | --- | --- |
| 109 | Write functional specifications and acceptance criteria for every extension before coding | Functional Lead | Custom governance | Approved specifications |
| 110 | Create isolated custom addons with manifests, access controls, translations and upgrade-safe inheritance | Development Lead | Custom | Installable modules |
| 111 | Add automated unit/transaction tests for discount, credit, quality, driver cash and transfer controls | Development Lead | Custom | Automated test evidence |
| 112 | Review performance and query behavior of cross-branch availability and customer history panels | Technical Lead | Custom | Performance benchmark |
| 113 | Test Arabic/English labels, RTL rendering, IQD/USD formats and printable documents | QA Lead | Standard + custom | Localization QA report |
| 114 | Perform code review, security review, dependency check and staging installation/upgrade test | Technical Lead | Custom | Release approval |
| 115 | Document configuration, custom modules, parameters, support diagnostics and rollback steps | Technical Lead | Custom | Technical runbook |

## P11 - Training, UAT, go-live and closure

| ID | Task | Responsible | Treatment | Deliverable / acceptance evidence |
| --- | --- | --- | --- | --- |
| 116 | Prepare role-based Arabic/English training guides and realistic door-trading exercises | Training Lead | Standard | Training materials |
| 117 | Train owners on dashboards, approvals, drill-down and exception monitoring | Training Lead | Standard | Owner attendance and assessment |
| 118 | Train seven accounting roles separately, including prohibited actions and handoffs | Training Lead | Standard | Accounting competency signoff |
| 119 | Train warehouse specialists on barcode, transfers, quality, dispatch, counts and discrepancies | Training Lead | Standard | Warehouse competency signoff |
| 120 | Train sales/POS users on attribute search, stock visibility, pricing, customer history and approvals | Training Lead | Standard | Sales competency signoff |
| 121 | Run conference-room pilot across complete order-to-cash, procure-to-pay and record-to-report cycles | QA Lead | Standard | Pilot issue log |
| 122 | Run formal UAT with client users, evidence, severity, retest and signed acceptance | Project Manager | Standard | UAT signoff |
| 123 | Complete go-live readiness review covering data, devices, users, controls, reports and support | Steering Committee | Standard | Go/no-go decision |
| 124 | Execute production cutover and validate first transactions at all three locations | Project Team | Standard | Day-one validation |
| 125 | Provide daily hypercare in week one, then agreed review cadence with severity-based SLA | Support Lead | Standard | Hypercare log |
| 126 | Reconcile first POS closures, driver handovers, stock transfers, bank/card receipts and accounting close | Chief Accountant | Standard | Post-go-live control signoff |
| 127 | Deliver administrator handover, as-built configuration, source code, test evidence and support runbook | Project Manager | Standard | Handover pack |
| 128 | Close critical issues, approve deferred backlog and obtain final project acceptance | Sponsor | Standard | Closure certificate |

# 6. Minimum end-to-end UAT scenario pack

- Retail POS cash sale with door, frame, accessory and trimming; correct tier price; passed quality; receipt and postings.

- Wholesale order for 15 doors across branches; 10% tier, reservation, transfer, delivery and invoice.

- Excess discount and credit breach; freeze, AR then Owner approval, rejection path.

- USD container purchase, partial receipt, landed costs, three-way match and FX payment.

- Manifest-driven Main-to-Branch transfer with transit and discrepancy.

- Failed quality moves to quarantine and blocks delivery/POS until passed recheck.

- COD delivery to driver box, counted handover, central vault transfer and variance.

- Customer 360 shows variant history, invoices, debt and credit limit.

- Bank/card import and reconciliation model proposes account, branch and analytics.

- Mock close reconciles stock, POS, driver cash, AR/AP, bank, tax, trial balance and branch P&L.

# 7. Training and client inputs

Training is separate for owners, each of the seven finance roles, the three inventory specialists, sales/POS users, and administrators. Completion requires attendance plus practical competency exercises, not attendance alone.

Required inputs include legal/tax data; approved chart of accounts; users and approval limits; product/variant/RAL/dimension/barcode data; opening stock and finance balances; quality rules; pricing and credit policies; POS/scanner hardware; card and bank formats; and signed tax treatment.

# 8. Assumptions, risks and final acceptance

- One Iraqi legal company and three warehouses/branches. Multi-company changes scope.

- Odoo 19 Enterprise and Odoo.sh are available; licenses, hardware and third-party integrations are commercial items unless included.

- No MRP, field installation, GPS, route optimization or eCommerce.

- Reference custom addons are not copied without separate specification, security review and approval.

- At least two migration rehearsals and a mock month-end close are mandatory.

- Final acceptance requires all 128 tasks completed/deferred by change control, no open critical issues, reconciled openings, signed security/control tests, training, UAT, handover and closure.